## Gantt Chart - latest
GANTT CHART | [9 empty] | Project Deliverables ➜ | [7 empty] | Develop a web-based Documents Development and Management application
| PROJECT TITLE |  | Online Document Development & Management - TechDocs | [6 empty] | Institutaion Name | [8 empty] | IIIT Hyderabad & Great Learning
| PROJECT MANAGER |  | Narayana Darapaneni | [6 empty] | DATE | [8 empty] | 2023-09-24
| Front End Team Lead |  | Avinash M Vetoskar, Srilatha Mummadi
| Back End Team Lead |  | Pradeep Suram, Soumava Moulik
| Deployment Team Lead |  | Narayana Kukunuri, Guruprasad Srinivasan, Sandeep Mishra
| Data Science Lead |  | Rajnish Kumar Ranjan
| WBS NUMBER | TASK TITLE | TASK OWNER | ADDITIONAL CONTRIBUTORS | COMMENTS | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE
[10 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
[10 empty] | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
| 1.1 | Project Management
| 1.1.1 | Project Architecture | Full Team
| 1.1.2 | Weekend tasks recommendation | All Leads
| 1.1.3 | Project Documentation | Aditya Bhatt, Buddha Hemanth
| 1.1.4 | Minutes of Meetings - Documentation | All Leads
| 1.1.5 | Project Management | Vennila Gunasekhar, Ritesh Biswal
| 1.2 | Frontend Team | Task Owner | Additional Contributors | Comments
| 1.2.1 | Flask structure and Flask templates, dockerization | Khadeeja Thameema, Abhishek Tenneti | [5 empty] | 100%
| 1.2.2 | Bootstrap theme - UX design Document | Satyam Bhardwaj | [5 empty] | 100%
| 1.2.3 | Welcome Screen - Home Page | Satyam Bhardwaj, Manjulekha M M | [5 empty] | 100%
| 1.2.4 | Sign-in page/Forgot password | Herin Gandhi, Thanu Krishnan T C | [5 empty] | 100%
| 1.2.5 | Registration page | Sugith Kumar Reddy Doddam reddy, Brundavani | [5 empty] | 100%
| 1.2.6 | User's Dashboard - Home | Ashish Barla, Pankaj Garg | [5 empty] | 100%
| 1.2.7 | Client side local storage | Mukesh Rajpurohit | [5 empty] | 100%
| 1.2.8 | Plans and subscriptions page | Suhaas Mahajan, Supriya Nayak, Herin Gandhi | [5 empty] | 100%
| 1.2.9 | Product features document page | Arjun Raj | [5 empty] | 100%
| 1.2.10 | Help and FAQ | Shilna Sasheendran, Prashanthi Kuna | [5 empty] | 100%
| 1.2.11 | User profile settings | Ashish Barla | [5 empty] | 100%
| 1.2.12 | Latex IDE page - editor, real time preview | Avinash M Vetoskar | [5 empty] | 100%
| 1.2.13 | Latex IDE page - history | Sugith Kumar Reddy | [5 empty] | 100%
| 1.2.14 | Latex IDE page - download as pdf | Mukesh Rajpurohit | [5 empty] | 100%
| 1.2.15 | Latex Templates (Resume and Blank) | Pankaj Garg | [5 empty] | 100%
| 1.2.16 | PWA manifest | Khadeeja Thameema | [5 empty] | 100%
| 1.2.17 | Service Worker | Shilna Sasheendran | [5 empty] | 100%
| 1.2.18 | Subscription Summary, Billling Details | Abhishek Tenneti, Ashish Barla | [5 empty] | 100%
| 1.2.19 | Logout | Thanu Krishnan T C | [5 empty] | 100%
| 1.2.20 | User's documents page - share document | Srilatha Mummadi | [5 empty] | 100%
| 1.2.21 | Trash | Praveen Maharana | [5 empty] | 100%
| 1.2.22 | Latex Templates (Resume and Blank) | Repeated content | [5 empty] | 100%
| 1.2.23 | Production Helper & Deployment Coordination | Prashanthi Kuna | [5 empty] | 100%
| 1.2.24 | Documentation | Praveen Maharana, Vibhaw Shankar | ] |  |  |  |  | 100%
| 1.2.25 | Code sanitation, integration, testing, fixing bugs | Vibhaw Shankar, Avinash M Vetoskar, Srilatha Mummadi | [5 empty] | 100%
| 1.3 | Backend Team | Task Owner | Additional Contributors | Comments
| 1.3.1 | ER diagram | Pradeep Suram | [5 empty] | 100%
| 1.3.2 | Database Schema - User authentication, profile, user access level (control) | Pradeep Suram | [5 empty] | 100%
| 1.3.3 | Database Schema - documents, history, payments/subscription | Pradeep Suram | [5 empty] | 100%
| 1.3.4 | User authentication - registration (admin user too) | Srikanth Rachoori | [5 empty] | 100%
| 1.3.5 | User authentication - logout | Pratheeka | [5 empty] | 100%
| 1.3.6 | User authentication - login user | Pradeep Suram | [5 empty] | 100%
| 1.3.7 | User authentication - delete user | Govind Rakesh Kumar, Ratnam Margana | [5 empty] | 100%
| 1.3.8 | User authentication - forgot password | Venkata Sai Krishna Potti | [5 empty] | 100%
| 1.3.9 | Payments/subscription | Soumava Moulik | [5 empty] | 100%
| 1.3.10 | Flask server setup and APIs for microservices | Shaik Saifullah, Soumava Moulik | [5 empty] | 100%
| 1.3.11 | Create file, modify file, update file, save file | Adithya kalapatapu | [5 empty] | 100%
| 1.3.12 | View file, delete file, download file, upload file | Adithya kalapatapu | [5 empty] | 100%
| 1.3.13 | Permission setting for access of files (file sharing) between users | Pratheeka | [5 empty] | 100%
| 1.3.14 | Compile the latex file to pdf | Venkata Sai Krishna Potti | [5 empty] | 100%
| 1.3.15 | Versioning and history | Srikanth Rachoori | [5 empty] | 100%
| 1.3.16 | Updating user profile | Bhuvaneshwar Kosaraju | [5 empty] | 100%
| 1.3.17 | Get user profile | Bhuvaneshwar Kosaraju, Shaik Saifullah | [5 empty] | 100%
| 1.3.18 | Change Password | Rajesh Sukumaran,Bhuvaneshwar Kosaraju | [5 empty] | 100%
| 1.3.19 | Dockerfile | Soumava Moulik | [5 empty] | 100%
| 1.3.20 | Code sanitation, integration, testing, fixing bugs | Soumava Moulik, Pradeep Suram | [5 empty] | 100%
| 1.3.21 | Documentation | Bhuvaneshwar Kosaraju | [5 empty] | 100%
| 1.4 | Deployment | Task Owner | Additional Contributors | Comments
| 1.4.1 | Git Hub - Tagging, Pull request approval process | Narayana Kukunuri | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.2 | Pushing the latest code changes to servers (Dev/Prod) | Narayana Kukunuri | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.3 | Deploying the latest code changes to dockers , Docker management | Narayana Kukunuri | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.4 | Front End server, Load Balancer - Creating AWS EC2 Linux instance, Creating security groups, Installing the Docker | Guruprasad Srinivasan | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.5 | Backend Server - Creating AWS EC2 Linux instance,Creating security groups, | Sandeep Mishra | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.6 | Installing the docker, Creating IAM users,allowing the users to access the SNS and S3 services access | Obillaneni Hemanth Raghavendra Krishna, Narayana Kukunuri | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.7 | Creating DNS , Creating the SSL Certificate | Pulkit Kumar Kukreja | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.8 | EBS Volume | Guruprasad Srinivasan, Sandeep Mishra | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.9 | Mysql RDS setup - Installation , Security group configuration | Guruprasad Srinivasan | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.10 | Cloud watch - Setting the services on all internal AWS services used in the architecture,Creating the alert settings | Ashwani Panwar, Sandeep Mishra | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.11 | Creating the SMTP settings for SNS | Narayana Kukunuri | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.12 | Connectiing all services and running them in a flow | Sandeep Mishra, Pradeep Suram | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.13 | Cloning the same setup for Production environment | Guruprasad Srinivasan, Rajnish Kumar Ranjan | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.14 | Deployment Documentation, MOM(Minutes of Meeting) | Vennila Gunasekhar, Ritesh Biswal | [5 empty] | 100% | bar: WEEK 2 Mo to WEEK 2 Su
| 1.4.15 | Code sanitation, integration, testing, fixing bugs | Obillaneni Hemanth , Ashwani Panwar
| 1.5 | Data Science | Task Owner | Additional Contributors | Comments
| 1.5.1 | Spelling and Grammar check | Rajnish Kumar Ranjan | [5 empty] | 100%
| 1.5.2 | Plagiarism check | Guruprasad Srinivasan | [5 empty] | 100%
| 1.5.3 | Helpdesk - chat/chatbot | Mohammad Abdul Rahmath | [5 empty] | 100%
| 1.5.4 | Sharing with external people (not registered on the tool) | Anirban Mukherjee | [5 empty] | 100%
| 1.5.5 | Product Analytics | Raghuram Kandarpa | [5 empty] | 100%
| 1.5.6 | Word suggestions | Mohan Prasath | [5 empty] | 100%
| 1.5.7 | Word meanings | Mohan Prasath | [5 empty] | 100%
| 1.5.8 | Document suggestions based on User's document history via Web scraping | Nikhil Sanjay Dhande, Gunturi Vaishnavi | [5 empty] | 100%
| 1.5.9 | Image to Word converter | Rajnish Kumar Ranjan, Kritika Goyal | [5 empty] | 100%
| 1.5.10 | Handling .doc, .ppt, .csv formats | Ritesh Biswal, Nikhil Sanjay Dhande | [5 empty] | 100%
| 1.5.11 | SSL certificate setup helps with enabling PWA capability & login using Gmail id | Pradeep Suram (Backend Team) | [5 empty] | 100%
| 1.5.12 | Network Failure checking & storing documents in LocalStroage until the network is restored | Pradeep Suram (Backend Team) | [5 empty] | 100%
| 1.5.13 | Upload images and other files | Mohammad Abdul Rahmath | [5 empty] | 100%
| 1.5.14 | Error pages, 4xx, 5xx, | Rajnish Kumar Ranjan, Raghuram Kandarpa | [5 empty] | 100%
| 1.5.15 | Email Templates - Welcome on Sign up | Kritika Goyal, Gunturi Vaishnavi | [5 empty] | 100%
| 1.5.16 | Email Templates - Reset Password | Kritika Goyal, Gunturi Vaishnavi | [5 empty] | 100%
| 1.5.17 | Email Template - On Sharing | Kritika Goyal, Gunturi Vaishnavi | [5 empty] | 100%
| 1.5.18 | Data pipeline for deployment | Narayana Kukunuri | [5 empty] | 100%
| 1.5.19 | Latex to PDF compile - backend | Soumava Moulik | [5 empty] | 100%
| 1.5.20 | Multi-user editing of documents | Soumava Moulik | [5 empty] | 100%
| 1.5.21 | Payment Gateway Integration | Soumava Moulik | [5 empty] | 100%
| 1.5.22 | Code sanitation, integration, testing, fixing bugs | Padavala Venkatesh, Yaqub Qureshi | [5 empty] | 100%
| 1.6 | Project Documentation | Task Owner | Additional Contributors | Comments
| 1.6.1 | Frontend Documentation | Aditya Bhatt, Buddha Hemanth, Nishant Atal, Brundavani, Shiva Tiwari, RAHUL P, Vangala Keerthana, sahithi yerramsetty | [5 empty] | 100%
| 1.6.2 | Backend Documentation | K.Satyapradeep, Sandra R Nair, Rajesh Sukumaran, Koushik Kumar Paul, Ankit Rawat, Shaik Farooq, | [5 empty] | 100%
| 1.6.3 | Deployment Documentation | Praveena Tumoju, Pravir Polly, Krishna Kumari Ragidimilli, T SHIVA KUMAR, Mayur pawar, SAMAHIT MAHAPATRA, K.R.JAYAPRADEEP | [5 empty] | 100%
| 1.6.4 | Data Science Documentation | Gundepudi Sai Bhavani, Indhusree Gorthi, Priyanshi Bhatnagar, Vamsi Varun Peddinti, Venkata M Gudala, Shikha | [5 empty] | 100%
| 1.7 | Tech Architecture | Task Owner | Additional Contributors | Comments
| 1.7.1 | Tech Architecture and stack research | Chappa Sasi Kumari, Avinash Kolluri, Aditya Bhatt, L Krishna Priya, Anish Misra | [5 empty] | 100%
| 1.7.2 | Tech Stack validation | Saraswata Mangal | [5 empty] | 100%
| 1.8 | Testing | Task Owner | Additional Contributors | Comments
0%
0%
0%
0%
0%
0%
0%
100%

## Gantt Chart - old (hidden)
GANTT CHART | [6 empty] | Project Deliverables ➜ | [7 empty] | Develop a web-based Documents Development and Management application
PROJECT TITLE |  | Online Document Development & Management - techDocs |  |  |  |  | Institutaion Name | [8 empty] | IIIT Hyderabad & Great Learning
PROJECT MANAGER |  | Prerna Waghray |  |  |  |  | DATE | [8 empty] | 2022-09-25
Front End Team Lead |  | Anil Kumar Beniwal
Back End Team Lead |  | Gaurav Pal
Deployment Team Lead |  | Akash Bansal
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
[7 empty] | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
1 | Week -1 |  | 2022-09-25 | 2022-10-01
1.1 | Project Management
1.1.1 | Project Architecture | Prerna Waghray, TLs | 2022-02-28 | 2022-03-06 | 0 | 0%
1.1.2 | Week2 tasks recommendation | Prerna Waghray, TLs |  |  | 0 | 0%
1.1.3 | Project Documentation | Shrey Soni, Kanchana Radhika Vashishta, Padmasree Sornapudi |  |  | 0 | 0%
1.1.4 | Minutes of Meetings - Documentation | Shrey Soni, Kanchana Radhika Vashishta, Padmasree Sornapudi |  |  | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
1.2 | Frontend
1.2.1. | Front End Architecture | Sai Srivally Thanneru, Anil Kumar Beniwal, Amrutha Karthikeyan |  |  | 0 | 0%
1.2.2 | Week2 tasks recommendation | Anil Kumar Beniwal |  |  | 0 | 0%
1.2.3 | Front End Fields Finalizaiton | Sreenivas Gundu |  |  | 0 | 0%
1.2.4 | Login Page ( https://www.overleaf.com/ ) | Eslavath vijay, Jagriti |  |  | 0 | 0%
1.2.5 | Subscription Plan Page ( https://www.overleaf.com/user/subscription/plans ) | Gowrigari Sravan Kumar Reddy, Krishna Manidhar J, Rajtilak Pattanaik |  |  | 0 | 0%
1.2.6 | Group Subscription ( https://www.overleaf.com/for/groups https://support.google.com/analytics/answer/1009702?hl=en#zippy=%2Cin-this-article ) | Juttu Ashish Varma, Rutwij Sanjeev Narsapur, Shrey Soni |  |  | 0 | 0%
1.2.7 | Sync with Google Drive, Dropbox, GitHub, GitLab, BitBucket ( https://www.overleaf.com/blog/195-new-collaborate-online-and-offline-with-overleaf-and-git-beta ) | Abhinav Singh, Sayantan Mukherjee, Sarith Madhu |  |  | 0 | 0%
1.2.8 | Usage Analytics | Sayantan Mukherjee, Srikala Kiranmayee |  |  | 0 | 0%
1.2.9 | Payment Module ( https://www.overleaf.com/user/subscription/plans ) | Kanchana Bharat Iyer, Yash Vij |  |  | 0 | 0%
1.2.10 | History | Siddharth Pandit, Agnibho Datta |  |  | 0 | 0%
1.2.11 | Share with others | Sulaiman Syed Irshad, Sowmya Chetty |  |  | 0 | 0%
1.2.12 | Front End Documentation | Shrey Soni, Anil Kumar Beniwal |  |  | 0 | 0%
1.2.13 | Analyse existing overleaf from frontend features & technolgies point of view https://www.overleaf.com/ https://github.com/overleaf/overleaf | Rajakanna, Titiksha Apte |  |  | 0 | 0%
1.2.14 | Expected features from AWS and cost | Vamsi Krishna, Thati Nishank |  |  | 0 | 0%
1.2.15 | Minutes of Meetings - Documentation | Shrey Soni, Anil Kumar Beniwal |  |  | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
1.3 | Backend
1.3.1. | Back End Architecture | Gaurav Pal, Radhika Vashishta, Ashwath Nagesh Belur |  |  | 0 | 0%
1.3.2 | Week2 tasks recommendation | Gaurav Pal, Ashwath Nagesh Belur |  |  | 0 | 0%
1.3.3. | Database fields finalization | Chaganti Chandrakala, GVV Satyanarayana Raju |  |  | 0 | 0%
1.3.4. | Database design | Janany Vaithyam Baskaran, PATHARDHELIZ NASEER |  |  | 0 | 0%
1.3.5 | Backend Documentation | Radhika Vashishta, Minakshi Trigunait |  |  | 0 | 0%
1.3.6 | Usage Analytics | Mohammad Aamir, Nishad Fulpagare, Pooja B |  |  | 0 | 0%
1.3.7 | Admin/User Table design (including different usage logs, payments, permissions, shares, submission, uploads, downloads, deletes etc) | Prerna Waghray, Rapthe Karthika |  |  | 0 | 0%
1.3.8 | Analyse existing overleaf from backend features & technolgies point of view https://www.overleaf.com/ https://github.com/overleaf/overleaf | Ria Jesmin, Shravan Kilaru, SIVA SANKARA RAO ANNAM |  |  | 0 | 0%
1.3.9 | Payment module backend logic | Nageswaraiah Abbannagari, Sneha kumari |  |  | 0 | 0%
1.3.10 | Sync with Google Drive, Dropbox, GitHub, GitLab, BitBucket ( https://www.overleaf.com/blog/195-new-collaborate-online-and-offline-with-overleaf-and-git-beta ) | Srikar Gullapalli, Uma Ponnalagu, Sruthi bargal |  |  | 0 | 0%
1.3.11 | History | Utkarsh Banyal, Venkat Sai Anurag, Altair Haque |  |  | 0 | 0%
1.3.12 | Share with others | Shreya Sood, Smitha B Shetty |  |  | 0 | 0%
1.3.13 | Analyse existing overleaf from backend features & technolgies point of view https://www.overleaf.com/ https://github.com/overleaf/overleaf | Kopparapu Vedasree, Namit Mohan Saxena |  |  | 0 | 0%
1.3.14 | Expected features from AWS and cost | S.Mugunthan, SaiGeetha Garikapati, |  |  | 0 | 0%
1.3.15 | Minutes of Meetings - Documentation | Shrey Soni, Radhika Vashishta |  |  | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
1.4 | Deployment
1.4.1. | Deployment Architecture | Akash Bansal, Upendra S Masade, Divyesh Bhatnagar |  |  | 0 | 0%
1.4.2 | Week2 tasks recommendation | Akash Bansal, Archana J Nambiar |  |  | 0 | 0%
1.4.3 | Deployment Plan | Akash Bansal, Sridevi Gara, Sri Harsha Mungara |  |  | 0 | 0%
14.4 | Github account activation | Prashanth Alluvada, Sri Ranga Valli Kottisi |  |  | 0 | 0%
1.4.5 | AWS account features identification and account activation. AWS account will be provided by Great Learning. Reach out to Suruchi once required account features identified | Ashwini Bhardwaj, Hardik Gaurangbhai Kothari, Manav Jayasingan, M Anand Kumar |  |  | 0 | 0%
1.4.6 | Analyse existing overleaf from deployment features & technolgies point of view https://www.overleaf.com/ https://github.com/overleaf/overleaf | Manav Jayasingan , Bhaskara Isukapalli, Rakshita.M, Prashanth Alluvada, M Anand Kumar |  |  | 0 | 0%
1.4.7 | Expected features from AWS and cost | M Anand Kumar, Kranthi Kumar Addepalli |  |  | 0 | 0%
1.4.8 | Deploy locally (in your laptop or desktop) the existing MVP https://github.com/overleaf/overleaf | diwakar Chandrasekaran, Harshal vishnoi, Josyula Ch T Naga Sai Pradeep, Prashanth Alluvada |  |  | 0 | 0%
1.4.9 | Deploy in the free AWS account, the existing MVP https://github.com/overleaf/overleaf | Rishabh Mutha, Shanthi Kiran Oleti, Sheetal PatneTADIKONDA V D PRASAD |  |  | 0 | 0%
1.4.10 | Deployment Documentation | Ravi Babu Madharam, Padmasree Sornapudi |  |  | 0 | 0%
1.4.15 | Minutes of Meetings - Documentation | Shrey Soni, Padmasree Sornapudi |  |  | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
2 | Week - 2 |  | 2022-10-02 | 2022-10-08 | 6
2.1 | Project Management
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
2.2 | Front End
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
2.3 | Backend
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
2.4 | Deployment
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
3 | Week - 3 |  | 2022-10-09 | 2022-10-15 | 6
3.1 | Project Management
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
3.2 | Front End
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
3.3 | Backend
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
3.4 | Deployment
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
4 | Week - 4 |  | 2022-10-16 | 2022-10-22 | 6
4.1 | Project Management
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
4.2 | Frontend
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
4.3 | Backend
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
4.4 | Deployment
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
0%
100%